## Sutton 28th June
Street | Town | Ward | Works location description | Works location | Work status | Activity type | Proposed start date | Proposed end date | Works reference number | Promoter | Promoter contact details | Traffic management type
REDHOUSE ROAD | BEDDINGTON | BEDDINGTON | Junction of Croydon Road to around 10m into Redhouse Road | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2024-07-22 | 2024-09-01 | XW200W120246784-05677 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
MEREBANK LANE | WALLINGTON | BEDDINGTON and WADDON | Junction with Stafford Road. | Carriageway | Works planned | Utility repair and maintenance works | 2024-07-25 | 2024-07-28 | XV057L24-STAFFORD-B | LAST MILE ELECTRICITY LIMITED (Formerly GLOBAL UTILITY CONNECTIONS) | 03300 587 622 | Road closure 07:00 - 19:00
STAFFORD ROAD | CROYDON | BEDDINGTON and WADDON | Junction with Merebank Lane | Carriageway | Works planned | Utility repair and maintenance works | 2024-07-25 | 2024-07-28 | XV057L24-STAFFORD-A | LAST MILE ELECTRICITY LIMITED (Formerly GLOBAL UTILITY CONNECTIONS) | 03300 587 622 | Two-way signals 07:00 - 19:00
AVENUE ROAD | BELMONT | BELMONT | Outside 12 | Carriageway | Works in progress | Immediate - urgent | 2024-06-25 | 2024-07-01 | DZ001J0G8D7 | SES WATER (Formerly SUTTON & EAST SURREY WATER COMPANY) | 01737 772000 | Multi-way signals 24hrs
DOWNS ROAD | SUTTON | BELMONT | Junction with Sutton Lane | Carriageway | Works planned | Highway repair and maintenance works | 2024-07-01 | 2024-07-02 | MB00898621187 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 20:00 - 05:00
BRIGHTON ROAD | SUTTON | BELMONT | Outside 251 - SM2 5ST | Carriageway | Works in progress | Immediate - urgent | 2024-06-20 | 2024-07-04 | XW063W120399301 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Two-way signals 24hrs
BANSTEAD ROAD SOUTH | SUTTON | BELMONT | Outside 15 | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2024-07-03 | 2024-07-09 | DZ001N0G1VR | SES WATER | 01737 772000 | Two-way signals 24hrs
DOWNS ROAD | SUTTON | BELMONT and BANSTEAD VILLAGE | Adjacent to Junction of Downs Road/Sutton Lane and Cotswold Road | Carriageway, Verge | Works planned | Highway repair and maintenance works | 2024-07-22 | 2024-07-23 | MB00279384945 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Multi-way signals 19:30 - 01:00
THE CRESCENT | BELMONT | BELMONT and CHEAM | at the junction with Belmont Rise - SM2 6BN | Carriageway | Works in progress | Immediate - urgent | 2024-06-26 | 2024-07-03 | XW063W120411893 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
GROSVENOR ROAD | WALLINGTON | CARSHALTON CENTRAL | Junction of Park Lane | Carriageway | Works planned | New service connection | 2024-07-09 | 2024-07-12 | KZ50053523485 | UK POWER NETWORKS | 0800 0280709 | Road closure 24hrs
ORCHARD WAY | SUTTON | CARSHALTON CENTRAL | Junction of Erskine Road | Carriageway | Works in progress | Immediate - urgent | 2024-06-12 | 2024-08-16 | XW200W120377572-02516 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
LITTLE WOODCOTE LANE | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Little Woodcote Lane X1 lamp column outside no. 56A | Footway, Verge | Works planned | Highway improvement works | 2024-06-29 | 2024-07-03 | MB00463724996 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Two-way signals 24hrs
MALDEN ROAD | CHEAM | CHEAM | 56-52 Malden Road Cheam Sutton Surrey Sutton SM3 8QF | Footway | Works planned | Utility asset works | 2024-07-01 | 2024-07-02 | BC008OGEA13940177 | BT | 03301 233753 | Two-way signals 09:30 - 15:30
MALDEN ROAD | CHEAM | CHEAM | 152 Malden Road Sutton SM3 8RA | Footway, Carriageway | Works planned | Disconnection or alteration of supply | 2024-07-23 | 2024-07-29 | KZ50024917850 | UK POWER NETWORKS SOUTH EASTERN | 0800 0280709 | Two-way signals 24hrs
DORCHESTER ROAD | MORDEN | ST. HELIER WEST | Green Lane to Borough Boundary | Carriageway | Works planned | Highway repair and maintenance works | 2024-07-26 | 2024-07-26 | MB00836814418 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
FOREST ROAD | SUTTON | STONECOT and WEST HELIER | Bridge over road BBJ 18 | Footway, Carriageway | Works planned | Works for Rail Purposes | 2024-07-28 | 2024-07-28 | KL815BBJ-18-00-280724 | NETWORK RAIL | 0345 711 4141 | Two-way signals 07:00 - 19:00
VALE ROAD | SUTTON | SUTTON NORTH | Junction with High Street to Junction with Bushey Lane | Footway, Carriageway | Works in progress | Statutory Infrastructure Works | 2024-01-29 | 2024-07-05 | DZ00107E4R | SES WATER | 01737 772000 | Road closure 24hrs
LANGLEY PARK ROAD | SUTTON | SUTTON SOUTH | Side of 39 Cedar Road | Carriageway | Works in progress | Immediate - urgent | 2024-06-27 | 2024-07-03 | DZ001J0G9V5 | SES WATER (Formerly SUTTON & EAST SURREY WATER COMPANY) | 01737 772000 | Multi-way signals 24hrs
EATON ROAD | SUTTON | SUTTON SOUTH | Junction of Cedar Road to Junction of Hilcroome Road | Carriageway | Works planned | New service connection | 2024-07-11 | 2024-07-12 | KZ50086866700 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
UPLAND ROAD | SUTTON | SUTTON SOUTH | Junction of Hilcroome Road to junction of Downside Road | Carriageway | Works in progress | New service connection | 2024-06-24 | 2024-07-12 | KZ50027701413 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
SHERWOOD PARK ROAD | SUTTON | SUTTON WEST & EAST CHEAM | Works to the side of No.67 on Sherwood Park Road | Footway | Works planned | Utility repair and maintenance works | 2024-07-04 | 2024-07-08 | DZ001J0G09F | SES WATER (Formerly SUTTON & EAST SURREY WATER COMPANY) | 01737 772000 | Multi-way signals 24hrs
ERSKINE ROAD | SUTTON | THE WRYTHE | Junction of Wrythe Lane to Junction of Erskine Close | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2024-04-08 | 2024-08-16 | XW200W119990117-02290 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BROOKFIELD AVENUE | SUTTON | THE WRYTHE & CARSHALTON CENTRAL | Junction of Wrythe Lane to approx 30m into Brookfield Avenue | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2024-01-22 | 2024-08-16 | XW200W119989300-02146 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
GROSVENOR AVENUE | CARSHALTON | WALLINGTON NORTH & CARSHALTON CENTRAL | Junction of Park Lane | Carriageway | Works planned | New service connection | 2024-07-04 | 2024-07-09 | KZ50000049431 | UK POWER NETWORKS | 0800 0280709 | Road closure 24hrs
WOODCOTE ROAD | WALLINGTON | WALLINGTON SOUTH | Outside 75 Woodcote Road. | Footway, Carriageway | Works planned | New service connection | 2024-07-08 | 2024-07-12 | DZ001N0F9MC | SES WATER | 01737 772000 | Two-way signals 24hrs
ONSLOW GARDENS | WALLINGTON | WALLINGTON SOUTH | Cornor of no.94 TO cornor of no.75 | Footway, Carriageway | Works planned | Utility asset works | 2024-07-17 | 2024-07-19 | BC310SOFAL00500339421212 | BT | 03301 233753 | Multi-way signals 24hrs
LINCOLN ROAD | WORCESTER PARK | WORCESTER PARK NORTH | Between Bridges Court & 1A/1B | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2024-07-01 | 2024-07-03 | MU091SLS00081354458-0045 | THAMES WATER | 0800 316 9800 | Road closure 24hrs
GREEN LANE | WORCESTER PARK | WORCESTER PARK NORTH | outside 42 outside The Green Primary School outside 72 Between 72 and Cumberland House outside 30 Green Lane Junc with Brookside | Carriageway | Works planned | Highway repair and maintenance works | 2024-07-03 | 2024-07-05 | MB00971939592 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Stop/go boards
LINCOLN ROAD | WORCESTER PARK | WORCESTER PARK NORTH | Outside and opposite Edge Court | Footway, Carriageway | Works planned | New service connection | 2024-07-01 | 2024-07-05 | KZ50066394379 | UK POWER NETWORKS SOUTH EASTERN | 0800 0280709 | Road closure 24hrs
RUSKIN DRIVE | WORCESTER PARK | WORCESTER PARK NORTH and SOUTH | Ruskin Drive, KT4 8LG - junction of Beverley Road and Cheam common Road. | Carriageway | Works planned | Utility asset works | 2024-07-19 | 2024-07-19 | MU026SA-656030-01 | THAMES WATER | 0800 316 9800 | Road closure 09:30 - 15:30