## WR_export_2024-05-31_09-04
Street | Town | Ward | Works location description | Works location | Work status | Activity type | Proposed start date | Proposed end date | Works reference number | Promoter | Promoter contact details | Traffic management type
BATH HOUSE ROAD | BEDDINGTON | BEDDINGTON | s/o unit 14 | Verge | Works planned | Utility repair and maintenance works | 2024-06-05 | 2024-06-06 | YN110STN010-PGN-MTR | EE Ltd | 01206 430321 | Two-way signals 24hrs
BEDDINGTON LANE | BEDDINGTON | BEDDINGTON | at tram level crossing- Beddington Lane- Just south of Brookmead Road | Carriageway | Works planned | Highway repair and maintenance works | 2024-06-01 | 2024-06-02 | YG60066795877 | TRANSPORT FOR LONDON (TFL) | 08456001703 | Two-way signals 01:00 - 05:00
BEDDINGTON LANE | BEDDINGTON | BEDDINGTON | between jct of Brookmead Road and Elberon Road. | Carriageway | Works planned | Highway repair and maintenance works | 2024-06-22 | 2024-06-23 | YG60038232246 | TRANSPORT FOR LONDON (TFL) | 08456001703 | Road closure 22:00 - 07:00
UPPER ROAD | WALLINGTON | BEDDINGTON | on the junction of sandy lane north and upper road | Carriageway | Works in progress | Immediate - urgent | 2024-05-24 | 2024-05-31 | DZ001J0FYLW | SES WATER | 01737 772000 | Road closure 24hrs
AVENUE ROAD | BELMONT | BELMONT | Dorset Road to Queens Road | Carriageway | Works in progress | Highway repair and maintenance works | 2024-05-30 | 2024-05-31 | MB00801525067 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00
COTSWOLD ROAD | SUTTON | BELMONT | O/S 34 to J/W Sutton Lane | Carriageway | Works planned | Highway improvement works | 2024-06-03 | 2024-06-14 | MB00887490624 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Multi-way signals 24hrs
CROSSWAYS | SUTTON | BELMONT | 42 | Footway | Works planned | Highway repair and maintenance works | 2024-06-03 | 2024-06-05 | MB00867401504 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure
DOWNS ROAD | SUTTON | BELMONT | O/S 67 to O/S 79 | Carriageway | Works planned | Highway improvement works | 2024-06-03 | 2024-06-14 | MB00812256781 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Multi-way signals 24hrs
BLAKEHALL ROAD | CARSHALTON | CARSHALTON CENTRAL | Jct of carshalton park road to junction of glebe road | Carriageway | Works in progress | New service connection | 2024-04-29 | 2024-06-21 | KZ50009305757 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
GLEBE ROAD | CARSHALTON | CARSHALTON CENTRAL | Junction of blakehall road to junction of grosvenor avenue | Carriageway | Works planned | New service connection | 2024-05-10 | 2024-06-21 | KZ50080583973 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
SHORTS ROAD | CARSHALTON | CARSHALTON CENTRAL | bridge over road BTH1 1233 | Carriageway | Works planned | Works for Rail Purposes | 2024-06-04 | 2024-06-05 | KL800BTH1-12-53-040624 | NETWORK RAIL | 0345 711 4141 | Road closure 22:00 - 06:00
WEST STREET | CARSHALTON | CARSHALTON CENTRAL | West Street, Bridge (Rail Over Road) No: 1232 | Carriageway | Works planned | Works for Rail Purposes | 2024-06-05 | 2024-06-06 | KL800BTH1-12-35-050624 | NETWORK RAIL | 0345 711 4141 | Road closure 22:00 - 06:00
PARK LANE | CARSHALTON | CARSHALTON CENTRAL & WALLINGTON NORTH | 63 to 71 | Carriageway | Works planned | Highway repair and maintenance works | 2024-05-31 | 2024-05-31 | MB00962394346 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Two-way signals 09:30 - 15:00
MALDEN ROAD | CHEAM | CHEAM | 80-94 Malden Road Cheam Sutton SM3 8QZ | Footway | Works planned | Utility asset works | 2024-06-04 | 2024-06-04 | BC008OGEA13152419 | BT | 03301 233753 | Two-way signals
TILEHURST ROAD | CHEAM | CHEAM | outside no 28 | Footway, Carriageway | Works in progress | Immediate - urgent | 2024-05-29 | 2024-06-04 | DZ001J0FNKG | SES WATER | 01737 772000 | Road closure 24hrs
MIDDLETON ROAD | CARSHALTON | ST HELIER EAST & WEST | In-between the Robertsbridge Road junction and the Tweed Dale/ Shaftsbury Road | Carriageway | Works planned | Utility repair and maintenance works | 2024-06-04 | 2024-06-04 | QU00152376107 | DFT ROAD STATISTICS DIVISION | 7971146101 | Two-way signals 09:30 - 14:30
GREEN WRYTHE CRESCENT | CARSHALTON | ST HELIER WEST | Outside number 7 - 12 Green Wruthey Crescent | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2024-06-25 | 2024-06-25 | YN10050996_ERI_STM_JW_RC | EE Ltd | 01206 430321 | Road closure 09:30 - 15:30
ST BENET'S GROVE | CARSHALTON | ST HELIER WEST | j/w stavordale road to robertsbridge road | Carriageway | Works planned | Highway repair and maintenance works | 2024-06-04 | 2024-06-04 | MB00910720418 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure
TEWKESBURY ROAD | CARSHALTON | ST HELIER WEST | j/w titchfield road to thornton road | Carriageway | Works planned | Highway repair and maintenance works | 2024-06-03 | 2024-06-03 | MB00917381372 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 24hrs
WESTMEAD ROAD | SUTTON | SUTTON CENTRAL | 89 -98 | Carriageway | Works planned | Highway improvement works | 2024-06-11 | 2024-06-18 | MB00858892537 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Multi-way signals 09:30 - 15:30
VALE ROAD | SUTTON | SUTTON NORTH | Junction with High Street to Junction with Bushey Lane | Footway, Carriageway | Works in progress | Statutory Infrastructure Works | 2024-01-29 | 2024-06-28 | DZ00107E4R | SES WATER | 01737 772000 | Road closure 24hrs
ALBION ROAD | SUTTON | SUTTON SOUTH | CW OS 18 & FW Opp (OS 25) - SM2 5TA | Footway, Carriageway | Works in progress | Immediate - emergency | 2024-05-07 | 2024-05-31 | XW063W120301581 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
HILLCROOME ROAD | SUTTON | SUTTON SOUTH | Junction of Eaton Road to junction of Upland Road | Carriageway | Works in progress | New service connection | 2024-04-02 | 2024-06-21 | KZ50046327968 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
UPLAND ROAD | SUTTON | SUTTON SOUTH | junction of hilcroome road to junction of downside road | Carriageway | Works planned | New service connection | 2024-06-17 | 2024-07-05 | KZ50027701413 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
FOOTPATH FROM BELMONT RISE TO SUMMERVILLE GARDENS | CHEAM | SUTTON WEST & EAST CHEAM | FP BELMONT RISE TO SUMMERVILLE GARDENS x2 LAMP COLS | Footpath | Works planned | Highway repair and maintenance works | 2024-06-03 | 2024-06-05 | MB00478549112 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Temporary obstruction 15 minute delay
ST JAMES' ROAD | SUTTON | SUTTON WEST & EAST CHEAM | S/o 29 Western Rd to Opposite 75 St James Rd | Footway, Carriageway | Works in progress | Statutory Infrastructure Works | 2024-01-08 | 2024-05-31 | DZ00107E67 | SES WATER | 01737 772000 | Two-way signals 24hrs
ERSKINE ROAD | SUTTON | THE WRYTHE | Junc Wrythe Lane to Junc Erskine Close | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2024-04-08 | 2024-06-10 | XW200W119990117-02290 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
GREEN WRYTHE LANE | CARSHALTON | THE WRYTHE | ADJ 27 AND OS 5 C/W ON, GREEN WRYTHE LANE | Footway, Carriageway | Works planned | Utility asset works | 2024-06-04 | 2024-06-04 | BC310SOFAL00500338671600 | BT | 03301 233753 | Multi-way signals
GREEN WRYTHE LANE | CARSHALTON | THE WRYTHE | OPP 28 to OPP 1 ON GREEN WRYTHE LANE, SM5 2DW | Footway, Carriageway | Works planned | Utility asset works | 2024-06-08 | 2024-06-08 | BC310SOFAL00500340137001 | BT | 03301 233753 | Multi-way signals 08:00 - 13:00
GREEN WRYTHE LANE | CARSHALTON | THE WRYTHE | OPP 30A | Carriageway | Works in progress | Utility repair and maintenance works | 2024-05-25 | 2024-06-05 | MU11300076800-00000003 | THAMES WATER | 0800 316 9800 | Two-way signals 24hrs
MILTON AVENUE | SUTTON | THE WRYTHE | OUTSIDE 74 | Carriageway | Works planned | Utility repair and maintenance works | 2024-06-04 | 2024-06-06 | DZ001J0FX4K | SES WATER | 01737 772000 | Multi-way signals 24hrs
WILLIAM STREET | CARSHALTON | THE WRYTHE | William Street JNC with Green Wrythe Lane | Carriageway | Works in progress | Utility repair and maintenance works | 2024-05-25 | 2024-06-05 | MU02600076800-00000003 | THAMES WATER | 0800 316 9800 | Road closure 24hrs
BROOKFIELD AVENUE | SUTTON | THE WRYTHE & CARSHALTON CENTRAL | Junc Wrythe Lane to approx 30m into Brookfield Avenue | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2024-01-22 | 2024-06-10 | XW200W119989300-02146 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
GREEN WRYTHE LANE | CARSHALTON | THE WRYTHE & ST HELIER WEST | Opposite Green Wrythe Crescent | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2024-06-26 | 2024-06-26 | YN10050996_ERI_STM_JW | EE Ltd | 01206 430321 | Two-way signals 09:30 - 14:30
CLYDE ROAD | WALLINGTON | WALLINGTON SOUTH | outside no 14 | Carriageway | Works in progress | Immediate - urgent | 2024-05-30 | 2024-06-05 | DZ001J0FYXM | SES WATER | 01737 772000 | Road closure 24hrs
BOSCOMBE ROAD | WORCESTER PARK | WORCESTER PARK NORTH | OUTSIDE 208 | Carriageway | Works planned | Utility repair and maintenance works | 2024-06-04 | 2024-06-06 | DZ001J0FW3M | SES WATER | 01737 772000 | Two-way signals 24hrs