## WR_export_2025-01-03_10-15
Street | Town | Ward | Works location description | Works location | Work status | Activity type | Proposed start date | Proposed end date | Works reference number | Promoter | Promoter contact details | Traffic management type
BEDDINGTON FARM ROAD | BEDDINGTON | BEDDINGTON | From jw Marlow Way to jw THERAPIA LANE | Carriageway | Works in progress | New service connection | 2024-09-09 | 2025-02-11 | KZ50042224514 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
COOMBER WAY | BEDDINGTON | BEDDINGTON | From adj 152 to JW BEDDINGTON LANE | Carriageway | Works planned | New service connection | 2025-01-30 | 2025-02-20 | KZ50075177995 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
COOMBER WAY | BEDDINGTON | BEDDINGTON | From os 1 COOMBER WAY to RB | Carriageway | Works planned | New service connection | 2025-01-13 | 2025-01-24 | KZ50093737743 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
STAFFORD ROAD | WALLINGTON | BEDDINGTON | 243, Stafford Road | Carriageway | Works planned | Permanent reinstatement | 2025-01-10 | 2025-01-10 | MU11300495217-00000002 | THAMES WATER | 0800 316 9800 | Two-way signals 09:30 - 14:30
EGMONT ROAD | SUTTON | BELMONT | Jct of Brighton Road to Jct of Devonshire Road | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2024-09-13 | 2025-02-14 | XW016W120366648-02284 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
HOMELAND DRIVE | SUTTON | BELMONT | j/w brighton road end (oneway section) | Carriageway | Works planned | Highway repair and maintenance works | 2025-01-15 | 2025-01-17 | MB00988080553 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Lane closure
THE DOWNSWAY | SUTTON | BELMONT | JO Brighton Road to JO Devonshire Road | Carriageway | Works planned | Utility repair and maintenance works | 2025-01-13 | 2025-02-14 | XW016W120897812-02669 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
THE HIGHWAY | SUTTON | BELMONT | The JO The Downsway to JO Heath Drive | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2024-10-28 | 2025-02-28 | XW016W120611923-02674 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
GROSVENOR AVENUE | CARSHALTON | CARSHALTON CENTRAL | Outside 54-20 | Carriageway | Works in progress | New service connection | 2024-11-11 | 2025-02-20 | KZ50017140623 | UK POWER NETWORKS | 0800 0280709 | Two-way signals 24hrs
HAROLD ROAD | SUTTON | CARSHALTON CENTRAL | Works at side of No.103 Westmead Road in Harold Road | Footway, Carriageway | Works planned | New service connection | 2025-01-06 | 2025-01-10 | DZ001N0H6DN | SES WATER | 01737 772000 | Road closure 24hrs
MILTON AVENUE | SUTTON | CARSHALTON CENTRAL | ENTIRE LENGTH | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2024-12-09 | 2025-01-31 | XW016W120499208-02477 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
ROTHERFIELD ROAD | CARSHALTON | CARSHALTON CENTRAL | s/o 77 Ruskin Rd | Footway, Carriageway | Works planned | Utility asset works | 2025-01-09 | 2025-01-09 | BC008WFJRDP0BSB01 | BT | 03301 233753 | Road closure 09:30 - 15:30
BANSTEAD ROAD | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | junction of downside road/waverley way | Footway, Carriageway | Works in progress | New service connection | 2024-12-07 | 2025-01-31 | KZ50056454715 | UK POWER NETWORKS | 0800 0280709 | Two-way signals 24hrs
CRANFIELD ROAD EAST | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Whole Length | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-01-02 | 2025-02-10 | XW016W120545706-02237 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
DOWNSIDE ROAD | SUTTON | CARSHALTON SOUTH & CLOCKHOUSE | outside no. 2 to junction of banstead road | Carriageway | Works planned | New service connection | 2025-01-20 | 2025-02-07 | KZ50022519507 | UK POWER NETWORKS | 0800 0280709 | Road closure 24hrs
PINE RIDGE | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Whole Length | Footway, Carriageway, Verge | Works in progress | Utility repair and maintenance works | 2024-12-02 | 2025-01-28 | XW016W120545695-02543 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
STANLEY ROAD | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | Junction with Cranfield Road East | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-01-02 | 2025-01-15 | XW016W120909036-02636 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
WAVERLEY WAY | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | junction of banstead road | Carriageway | Works planned | New service connection | 2025-01-20 | 2025-01-31 | KZ50011695295 | UK POWER NETWORKS | 0800 0280709 | Road closure 24hrs
WOODMANSTERNE ROAD | CARSHALTON | CARSHALTON SOUTH & CLOCKHOUSE | 40 METRES SOUTH OF ENTRANCE RD TO LITTLE WOODCOTE ESTATE | Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-01-19 | 2025-01-19 | BC008PTMS541130 | BT | 03301 233753 | Road closure 09:30 - 15:30
MALDEN ROAD | CHEAM | CHEAM | Outside of 138 | Carriageway | Works planned | Utility asset works | 2025-01-14 | 2025-01-14 | BC008OGEA793193812WSB | BT | 03301 233753 | Two-way signals 09:30 - 15:30
MALDEN ROAD | CHEAM | CHEAM | Outside of 72 | Footway, Carriageway | Works planned | Utility asset works | 2025-01-05 | 2025-01-05 | BC008OGEA15005283TW | BT | 03301 233753 | Two-way signals 09:00 - 15:30
POND HILL GARDENS | CHEAM | CHEAM | Outside 16 | Footway, Carriageway | Works planned | Utility asset works | 2025-01-27 | 2025-01-28 | BC008OGEA12875253SBRC | BT | 03301 233753 | Road closure 09:30 - 15:30
LONDON ROAD | HACKBRIDGE | HACKBRIDGE | Outside property 19 | Carriageway | Works planned | Utility repair and maintenance works | 2025-01-05 | 2025-01-05 | MU11300694318-00000002 | THAMES WATER | 0800 316 9800 | Multi-way signals 09:30 - 15:30
GLYN ROAD | WORCESTER PARK | NORTH CHEAM | Works outside and opposite No.13 | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-01-08 | 2025-01-14 | DZ001N0HJJ2 | SES WATER | 01737 772000 | Multi-way signals 24hrs
PLOUGH LANE | PURLEY | SOUTH BEDDINTON & ROUNDSHAW | Opposite the junction with Foresters Drive | Carriageway, Verge | Works planned | Utility asset works | 2025-01-16 | 2025-01-20 | P600214174523-WHP-LS | Cornerstone Telecommunications Infrastructure Limited | 01206 430321 | Multi-way signals 09:30 - 14:30
SANDY LANE SOUTH | WALLINGTON | SOUTH BEDDINTON & ROUNDSHAW | Junc Wordsworth Road - SM6 9QZ | Carriageway | Works in progress | Immediate - emergency | 2024-12-31 | 2025-01-08 | XW063W120948734 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
WORDSWORTH ROAD | WALLINGTON | SOUTH BEDDINTON & ROUNDSHAW | Junc Sandy Lane South - SM6 9QZ | Carriageway | Works in progress | Immediate - emergency | 2024-12-31 | 2025-01-08 | XW063W120948734-1 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
MIDDLETON ROAD | CARSHALTON | ST HELIER WEST | approx 20m westbound of Shaftsbury road | Carriageway | Works planned | Statutory Infrastructure Works | 2025-01-06 | 2025-01-06 | YG50451253730 | TRANSPORT FOR LONDON (TFL) | 08456001703 | Two-way signals 19:00 - 23:00
MANOR LANE | SUTTON | SUTTON CENTRAL | Works outside and opposite No.8A | Footway, Carriageway | Works planned | New service connection | 2025-01-13 | 2025-01-17 | DZ001N0H1HQA | SES WATER | 01737 772000 | Road closure 24hrs
WESTMEAD ROAD | SUTTON | SUTTON CENTRAL | ENTIRE LENGTH | Footway, Carriageway | Works in progress | Utility repair and maintenance works | 2025-01-02 | 2025-02-06 | XW016W120499050-02747 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Multi-way signals 24hrs
HIGH STREET | SUTTON | SUTTON NORTH | O/S No 366 | Footway | Works planned | Utility asset works | 2025-01-13 | 2025-01-15 | RE002SUT7000DD-RM-WK02 | IPM COMMS | 02083267782 | Two-way signals 24hrs
HILLCROOME ROAD | SUTTON | SUTTON SOUTH | junction of eaton road to junction of upland road | Carriageway | Works planned | New service connection | 2025-01-06 | 2025-02-03 | KZ50046327968 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
HILLCROOME ROAD | SUTTON | SUTTON SOUTH | 2b Hillcroome Road | Carriageway | Works planned | Utility asset works | 2025-01-06 | 2025-01-08 | DZ001J0GKGK | SES WATER | 01737 772000 | Multi-way signals 24hrs
LANGLEY PARK ROAD | SUTTON | SUTTON SOUTH | to the side of 37 Cedar Road | Footway, Carriageway | Works planned | New service connection | 2025-01-13 | 2025-01-24 | KZ50046106332 | UK POWER NETWORKS | 0800 0280709 | Multi-way signals 24hrs
LANGLEY PARK ROAD | SUTTON | SUTTON SOUTH | SIDE OF NO. 37 CEDAR ROAD | Footway, Carriageway | Works planned | New service connection | 2025-01-06 | 2025-01-08 | DZ001N0G1J4 | SES WATER | 01737 772000 | Two-way signals 24hrs
BOUNDARY ROAD | CARSHALTON | WALLINGTON SOUTH | J/W Stanley Park Road - J/W Briar Lane | Footway, Carriageway | Works planned | Utility repair and maintenance works | 2025-01-27 | 2025-04-07 | XW016W120739910-05396 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BRAMBLEDOWN ROAD | CARSHALTON | WALLINGTON SOUTH | J/W Boundary Road - J/W Mount Park | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-01-02 | 2025-02-03 | XW016W120545542-02133 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BRIAR BANKS | CARSHALTON | WALLINGTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-01-27 | 2025-02-17 | XW016W120545598-02138 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
BRIAR LANE | CARSHALTON | WALLINGTON SOUTH | Whole Length | Footway, Carriageway, Verge | Works planned | Utility repair and maintenance works | 2025-01-20 | 2025-02-21 | XW016W120545634-02139 | SOUTHERN GAS NETWORKS PLC | 0800 912 1700 | Road closure 24hrs
LONGFELLOW ROAD | WORCESTER PARK | WORCESTER PARK NORTH | o/s 268 | Footway | Works planned | Highway improvement works | 2025-01-06 | 2025-04-25 | MB01311744034 | LONDON BOROUGH OF SUTTON | 0208 547 5000 | Road closure 08:00 - 17:00